{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Faq"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Faq","index":0,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["N.ro","Domanda","Risposta"]
[1,"In merito alla procedura in corso si chiede quanto segue:\r\nI tempi di esecuzione lavori riportati nel Disciplinare di gara (Pag.23 puntoC2) ammontano a 225 giorni mentre nel Bando di gara (Pag. 3 punti II.3) ammontano a 180 giorni.\r\nIl ribasso sul tempo di esecuzione lavori su quanti giorni deve essere applicato?\r\nIn attesa di un Vs riscontro si porgono cordiali saluti.","il tempo di esecuzione è pari a 180 giorni in aderenza a quanto riportato nel bando di gara, nel disciplinare di gara a pag. 39 lettera b) valutazione dell'offerta tempo, e nel capitolato speciale d'appalto allegato al progetto esecutivo  pag. 13 art. 12.  Quanto riportato nel disciplinare di gara a pag. 3 punti II.3 è il risultato di un mero refuso pertanto, leggasi 180 giorni."]